## Door Schedule
RAC INC. ¦ OAK VALLEY ESTATES LOT 5 – RODRIGUEZ RESIDENCE ¦ DOOR SCHEDULE
Sunpro St George: 3781 S River Rd, St George UT 84790 ¦ Ph: 435-634-2220 ¦ Kevin Gill: 435-669-5347 ¦ TruStile Acct Mgr: Paris Raymond ¦ Existing Quote: SQAQGI000175-1 (UPDATE REQUIRED) ¦ Prepared: March 05, 2026
Mark | Level | Room / Location | Plan Tag | TruStile Model | Style | Material | Finish/Color | Door W | Door H | Thick. | RO Width | RO Height | Leaf Config | Fire Rating | Jamb Type | Notes | Status
▶ MAIN LEVEL
D-ML-01 | Main Level | Entry / Foyer (Exterior) | DOOR 4 | TMF1000 | Flush MDF | MDF | Bright Gray | 3'-0" | 8'-0" | 1-3/4" | 3'-2" | 8'-2" | Single Swing | Non-Rated | Ext – Pine Rabbet + WS | Exterior entry. Kerf. Bronze WS. ORB hinges. Design code: EICnMYsYv | ⚠️ CONFIRM SIZE
D-ML-02 | Main Level | Entry Closet | DOOR 2 | TMF1000 | Flush MDF | MDF | Off-White | 2'-6" | 8'-0" | 1-3/4" | 2'-8" | 8'-2" | Single Swing | Non-Rated | Int – Poplar Flat | ORB hinges. Design code: 1tRmHbBwT | ⚠️ CONFIRM SIZE
D-ML-03 | Main Level | Great Room / Living | DOOR 2 | TMF1000 | Flush MDF | MDF | Off-White | 3'-0" | 8'-0" | 1-3/4" | 3'-2" | 8'-2" | Single Swing | Non-Rated | Int – Poplar Flat | ORB hinges. Design code: 1tRmHbBwT | ⚠️ CONFIRM SIZE
D-ML-04 | Main Level | Kitchen | DOOR 2 | TMF1000 | Flush MDF | MDF | Off-White | 2'-6" | 8'-0" | 1-3/4" | 2'-8" | 8'-2" | Single Swing | Non-Rated | Int – Poplar Flat | ORB hinges. Design code: 1tRmHbBwT | ⚠️ CONFIRM SIZE
D-ML-05 | Main Level | Pantry | DOOR 2 | TMF1000 | Flush MDF | MDF | Off-White | 2'-6" | 8'-0" | 1-3/4" | 2'-8" | 8'-2" | Single Swing | Non-Rated | Int – Poplar Flat | ORB hinges. Design code: 1tRmHbBwT | ⚠️ CONFIRM SIZE
D-ML-06 | Main Level | Dining Room | DOOR 2 | TMF1000 | Flush MDF | MDF | Off-White | 3'-0" | 8'-0" | 1-3/4" | 3'-2" | 8'-2" | Single Swing | Non-Rated | Int – Poplar Flat | ORB hinges. Design code: 1tRmHbBwT | ⚠️ CONFIRM SIZE
D-ML-07 | Main Level | Office | DOOR 1 | FL100 | Full-Lite Glass | MDF | Bright Gray | 3'-0" | 8'-0" | 1-3/4" | 3'-2" | 8'-2" | Single Swing | Non-Rated | Int – Poplar Flat | Clear glass. ORB hinges. Design code: C8ZT9dSob | ⚠️ CONFIRM SIZE
D-ML-08 | Main Level | Office Closet | DOOR 2 | TMF1000 | Flush MDF | MDF | Off-White | 2'-0" | 8'-0" | 1-3/4" | 2'-2" | 8'-2" | Single Swing | Non-Rated | Int – Poplar Flat | ORB hinges. Design code: 1tRmHbBwT | ⚠️ CONFIRM SIZE
D-ML-09 | Main Level | Office Bath | DOOR 3 | TS1000 | Shaker Panel | MDF | Bright Gray | 2'-6" | 8'-0" | 1-3/4" | 2'-8" | 8'-2" | Single Swing | Non-Rated | Int – Poplar Flat | One-step OS sticking. ORB hinges. Design code: Au31tRnqMY | ⚠️ CONFIRM SIZE
D-ML-10 | Main Level | Powder Bath | DOOR 3 | TS1000 | Shaker Panel | MDF | Bright Gray | 2'-6" | 8'-0" | 1-3/4" | 2'-8" | 8'-2" | Single Swing | Non-Rated | Int – Poplar Flat | One-step OS sticking. ORB hinges. Design code: Au31tRnqMY | ⚠️ CONFIRM SIZE
D-ML-11 | Main Level | Garage (House-to-Garage) | DOOR 4 | TMF1000 | Flush MDF | MDF | Bright Gray | 3'-0" | 8'-0" | 1-3/4" | 3'-2" | 8'-2" | Single Swing | 20-Min FR | Ext – Pine Rabbet + WS | Fire-rated. Kerf. Bronze WS. VERIFY kerf/hardware compatibility. Design code: EICnMYsYv | ⚠️ CONFIRM SIZE
▶ UPPER LEVEL
D-UL-01 | Upper Level | Primary Suite Entry | DOOR 1 | FL100 | Full-Lite Glass | MDF | Bright Gray | 3'-6" | 8'-0" | 1-3/4" | 3'-8" | 8'-2" | Double / Pair | Non-Rated | Int – Poplar Flat | Clear glass pair. Magnetic catch. ORB hinges. Design code: C8ZT9dSob | ⚠️ CONFIRM SIZE
D-UL-02 | Upper Level | Primary Bath | DOOR 3 | TS1000 | Shaker Panel | MDF | Bright Gray | 2'-6" | 8'-0" | 1-3/4" | 2'-8" | 8'-2" | Single Swing | Non-Rated | Int – Poplar Flat | One-step OS sticking. ORB hinges. Design code: Au31tRnqMY | ⚠️ CONFIRM SIZE
D-UL-03 | Upper Level | Primary Closet | DOOR 2 | TMF1000 | Flush MDF | MDF | Off-White | 2'-6" | 8'-0" | 1-3/4" | 2'-8" | 8'-2" | Single Swing | Non-Rated | Int – Poplar Flat | ORB hinges. Design code: 1tRmHbBwT | ⚠️ CONFIRM SIZE
D-UL-04 | Upper Level | Upper Laundry | DOOR 3 | TS1000 | Shaker Panel | MDF | Bright Gray | 2'-6" | 8'-0" | 1-3/4" | 2'-8" | 8'-2" | Single Swing | Non-Rated | Int – Poplar Flat | One-step OS sticking. ORB hinges. Design code: Au31tRnqMY | ⚠️ CONFIRM SIZE
▶ BASEMENT
D-BM-01 | Basement | Basement Living / Theater | DOOR 2 | TMF1000 | Flush MDF | MDF | Off-White | 3'-0" | 8'-0" | 1-3/4" | 3'-2" | 8'-2" | Single Swing | Non-Rated | Int – Poplar Flat | ORB hinges. Design code: 1tRmHbBwT | ⚠️ CONFIRM SIZE
D-BM-02 | Basement | Basement Storage | DOOR 2 | TMF1000 | Flush MDF | MDF | Off-White | 3'-0" | 8'-0" | 1-3/4" | 3'-2" | 8'-2" | Single Swing | Non-Rated | Int – Poplar Flat | ORB hinges. Design code: 1tRmHbBwT | ⚠️ CONFIRM SIZE
D-BM-03 | Basement | Basement Bath | DOOR 3 | TS1000 | Shaker Panel | MDF | Bright Gray | 2'-6" | 8'-0" | 1-3/4" | 2'-8" | 8'-2" | Single Swing | Non-Rated | Int – Poplar Flat | One-step OS sticking. ORB hinges. Design code: Au31tRnqMY | ⚠️ CONFIRM SIZE
D-BM-04 | Basement | Gun Range / Gun Room | DOOR 4 | TMF1000 | Flush MDF | MDF | Bright Gray | 3'-6" | 8'-0" | 1-3/4" | 3'-8" | 8'-2" | Single Swing | Non-Rated | Ext – Pine Rabbet | Kerf. ORB hinges. Design code: EICnMYsYv | ⚠️ CONFIRM SIZE
D-BM-05 | Basement | Panic Room | SPECIAL | N/A – Ballistic | Vault Style | Steel | N/A | TBD | TBD | TBD | TBD | TBD | Single Swing | Ballistic | Vault Frame | Brown Safe Estate 8030 or equiv. Separate order – NOT TruStile. | ⚠️ SPEC TBD
▶ ADU / CASITA
D-AD-01 | ADU / Casita | ADU Living (Exterior Entry) | DOOR 4 | TMF1000 | Flush MDF | MDF | Bright Gray | 3'-0" | 8'-0" | 1-3/4" | 3'-2" | 8'-2" | Single Swing | Non-Rated | Ext – Pine Rabbet + WS | Exterior. Kerf. Bronze WS. ORB hinges. Design code: EICnMYsYv | ⚠️ CONFIRM SIZE
D-AD-02 | ADU / Casita | ADU Kitchen | DOOR 2 | TMF1000 | Flush MDF | MDF | Off-White | 2'-6" | 8'-0" | 1-3/4" | 2'-8" | 8'-2" | Single Swing | Non-Rated | Int – Poplar Flat | ORB hinges. Design code: 1tRmHbBwT | ⚠️ CONFIRM SIZE
D-AD-03 | ADU / Casita | ADU Bath 1 | DOOR 3 | TS1000 | Shaker Panel | MDF | Bright Gray | 2'-6" | 8'-0" | 1-3/4" | 2'-8" | 8'-2" | Single Swing | Non-Rated | Int – Poplar Flat | One-step OS sticking. ORB hinges. Design code: Au31tRnqMY | ⚠️ CONFIRM SIZE
D-AD-04 | ADU / Casita | ADU Bedroom | DOOR 2 | TMF1000 | Flush MDF | MDF | Off-White | 2'-6" | 8'-0" | 1-3/4" | 2'-8" | 8'-2" | Single Swing | Non-Rated | Int – Poplar Flat | ORB hinges. Design code: 1tRmHbBwT | ⚠️ CONFIRM SIZE
TOTAL DOOR COUNT (excl. Panic Room special) | [7 empty] | 23
LEGEND: DOOR 1=FL100 Full-Lite Glass (Bright Gray) ¦ DOOR 2=TMF1000 Flush (Off-White, interior) ¦ DOOR 3=TS1000 Shaker Panel (Bright Gray, wet rooms) ¦ DOOR 4=TMF1000 Flush (Bright Gray, exterior/garage) ¦ All TruStile: MDF 1-3/4" thick 8'-0" ht US10B ORB hinges ¦ RO=door size+2"W/+2"H ¦ ⚠️=verify from Revit before ordering

## Sunpro Procurement
SUNPRO ST GEORGE – PROCUREMENT SUMMARY ¦ RODRIGUEZ RESIDENCE
Sunpro St George ¦ 3781 S River Rd St George UT 84790 ¦ 435-634-2220 ¦ Kevin Gill 435-669-5347 ¦ TruStile Acct Mgr: Paris Raymond ¦ Existing Quote SQAQGI000175-1 (08/29/2025) – TMF2200 basis – UPDATE REQUIRED
UPDATED DOOR TYPE SUMMARY – BY MODEL
Plan Tag | TruStile Model | Style | Material | Finish | Thickness | Height | Sticking | Glass | Fire Rating | Design Code | Est. Qty
DOOR 1 | FL100 | Full-Lite Glass | MDF | Bright Gray | 1-3/4" | 8'-0" | One Step (OS) | Clear | Non-Rated | C8ZT9dSob | 2
DOOR 2 | TMF1000 | Flush | MDF | Off-White | 1-3/4" | 8'-0" | N/A (Flush) | None | Non-Rated | 1tRmHbBwT | 11
DOOR 3 | TS1000 | Shaker Panel | MDF | Bright Gray | 1-3/4" | 8'-0" | One Step (OS) | None | Non-Rated | Au31tRnqMY | 7
DOOR 4 | TMF1000 | Flush Ext. | MDF | Bright Gray | 1-3/4" | 8'-0" | N/A (Flush) | None | 20-Min FR (garage) | EICnMYsYv | 4
SPECIAL | N/A | Vault/Ballistic | Steel | N/A | N/A | TBD | N/A | N/A | Ballistic | N/A | 1
EXISTING QUOTE SQAQGI000175-1 (TMF2200 Basis – DO NOT ORDER – UPDATE REQUIRED)
Line | Qty | UOM | Description | Size | Config | Fire Rating | Unit $ | Extended $ | Notes
1 | 4 | EA | 29-13/16" x 96" TMF2200 Swing Single, Prehung, Kerf, Bevel Lock RH, Prime, Wedge | 29-13/16" x 96" | Single Swing | Non-Rated | $1,070.22 | $4,280.86 | ⚠️ Update – new door types
2 | 7 | EA | 35-13/16" x 96" TMF2200 Swing Single, Prehung, Kerf, Bevel Lock RH, Prime, Wedge | 35-13/16" x 96" | Single Swing | Non-Rated | $1,088.26 | $7,617.83 | ⚠️ Update – new door types
3 | 8 | EA | 31-13/16" x 96" TMF2200 Slab Only, Single, Kerf, Bevel Lock RH, Prime, Wedge | 31-13/16" x 96" | Slab Only | Non-Rated | $863.86 | $6,910.89 | ⚠️ Update – new door types
4 | 3 | EA | 35-13/16" x 96" TMF2200 Swing Single, Prehung, Kerf, 20-Min FR, Unknown Handing | 35-13/16" x 96" | Single Swing | 20-Min FR | $2,302.85 | $6,908.54 | ⚠️ DOOR 4; confirm handing
5 | 1 | EA | 35-13/16" x 96" per leaf TMF2200 Swing Pair, Prehung, Kerf, Bevel Meeting Stiles | 35-13/16" ea. | Pair | Non-Rated | $2,196.92 | $2,196.92 | ⚠️ Update to DOOR 1 pair
6 | 1 | EA | Manufacturer Freight for 24 Doors | — | — | — | $300.00 | $300.00 | Retain – re-quote for new order
ORIGINAL QUOTE TOTAL – DO NOT ORDER | [7 empty] | $28,215.05
ACTION ITEMS – REQUIRED BEFORE PLACING NEW ORDER WITH SUNPRO / TRUSTILE
1 | Confirm all rough opening sizes from updated Revit plans before submitting new order
2 | Request updated quote from Sunpro using new door types: FL100, TMF1000 Off-White, TS1000, TMF1000 Bright Gray – reference TruStile design codes on this sheet
3 | Confirm handing (LH/RH) for every door – existing quote flags Unknown Handing on fire-rated door (Line 4)
4 | Confirm primary suite entry config: pair vs. single leaf; confirm glass spec for FL100 (clear vs. obscure)
5 | Garage house-to-garage: confirm 20-min fire rating still required under DOOR 4 spec
6 | Panic room ballistic door: obtain separate spec/quote (Brown Safe or equiv) – NOT in TruStile order
7 | Verify kerf placement on all fire-rated doors (TruStile warning noted on Line 4 of existing quote)
8 | Lead time 7-8 weeks from confirmed PO – align order date with framing/finish milestone

## TruStile Spec Reference
TRUSTILE DOOR SPEC REFERENCE – RODRIGUEZ RESIDENCE
Source: TruStile Door Visualizer exports (Door_1–4 PDFs) + Quote SQAQGI000175-1 ¦ All doors: MDF 1-3/4" thick 8'-0" ht US10B ORB hinges ¦ Jamb: 4-9/16" Ogee Applied (int), Pine Rabbet (ext)
Plan Tag | Model | Series | Style | Sticking | Panel | Glass | Material | Finish | Fire Rating | Design Code | Visualizer Link | Hinges | Jamb Spec | Lead Time | Notes
DOOR 1 | FL100 | TS Series | Full-Lite Glass | One Step (OS) | N/A | Clear | MDF | Bright Gray | Non-Rated | C8ZT9dSob | https://www.trustile.com/interior-doors/fl-series/fl100 | 4x4 sq, US10B ORB | Poplar Paint-Grade, 4-9/16", Ogee Applied | 7-8 wks | Primary suite & office. Full-height clear glass panel. Magnetic catch on pair. Confirm: single vs. pair per Revit.
DOOR 2 | TMF1000 | TS Series | Flush MDF | N/A (Flush) | N/A | None | MDF | Off-White | Non-Rated | 1tRmHbBwT | https://www.trustile.com/interior-doors/tmf-series/tmf1000 | 4x4 sq, US10B ORB | Poplar Paint-Grade, 4-9/16", Ogee Applied | 7-8 wks | Standard interior flush. All general living/bedroom/closet rooms. Off-White painted finish.
DOOR 3 | TS1000 | TS Series | Shaker Panel | One Step (OS) | Flat (C) | None | MDF | Bright Gray | Non-Rated | Au31tRnqMY | https://www.trustile.com/interior-doors/ts-series/ts1000 | 4x4 sq, US10B ORB | Poplar Paint-Grade, 4-9/16", Ogee Applied | 7-8 wks | Wet rooms & laundry. Single flat panel with one-step sticking profile. Bright Gray painted finish.
DOOR 4 | TMF1000 | TS Series | Flush MDF – Ext. | N/A (Flush) | N/A | None | MDF | Bright Gray | 20-Min FR (garage) | EICnMYsYv | https://www.trustile.com/interior-doors/tmf-series/tmf1000 | 4x4 sq, US10B ORB | Pine Rabbet Primed, 4-9/16", Kerf for WS | 7-8 wks | Exterior & garage entries. Kerf. Bronze WS (QLON 97"). Composite adjustable sill. Garage leaf: 20-min fire-rated.
SUNPRO CONTACT & ORDER INFORMATION
Supplier | Sunpro – St George (St George Garage Doors)
Address | 3781 S River Rd, St George, UT 84790
Phone | 435-634-2220
Sales Contact | Kevin Gill ¦ 435-669-5347
TruStile Acct Mgr | Paris Raymond
TruStile Phone/Fax | 888-286-3931 ¦ Fax: 888-288.6521
TruStile Address | 1111 E. 71st Ave, Denver, CO 80229
Existing Quote # | SQAQGI000175-1 (dated 08/29/2025 – TMF2200 basis)
Existing Quote Total | $28,215.05 – DO NOT ORDER; new door types required
Lead Time | 7-8 weeks from confirmed purchase order
Freight (original) | $300.00 for 24 doors – re-quote for updated order