CHANGE ORDER

CO-001-7

(Supersedes and Replaces CO-001 and CO-007 — St. George Windows)

| PROJECT Rodriguez Residence — Oak Valley Estates Lot 5 646 W Liberty Lane, Kanarraville, UT 84742 OWNER ARJR Kanarraville Holdings, LLC Jessica and Adrian Rodriguez | CONTRACTOR RAC Inc. — Craig Engel racinc19@gmail.com ¦ 435-229-7350 CO NUMBER CO-001-7 DATE: March 15, 2026 |
| --- | --- |

SUPERSESSION NOTICE This Change Order CO-001-7 supersedes and fully replaces the following previously approved change orders, which are hereby voided and subsumed herein: • CO-001 — Glass Door Automation, Saint George Glass ($20,038.95, approved 2026-02-20 by Jessica Rodriguez) — VOIDED • CO-007 (STG) — Retractable Screens, St. George Windows ($23,869.90, approved 2026-03-03 by Adrian Rodriguez) — VOIDED Both CO-001 and CO-007 (STG) were previously approved and are included in the approved CO total of $113,344.85. This CO-001-7 adds only the net new amount above those previously approved sums: the glass package price increase of $37,414.80, for a net new addition to the contract of $37,414.80.

# SCOPE OF WORK

This Change Order covers the following three scope items, consolidated from CO-001, CO-007 (STG), and new scope:

1.  GLASS PACKAGE PRICE ADJUSTMENT (NET NEW SCOPE) — The aluminum window and door package (Strata Windows & Doors / St. George Windows) was revised from the initial quotation ($237,691.65) to the current confirmed estimate — Est. #3692, Oct. 30, 2025 ($275,106.45). Changes include glass specification upgrade from Low-E 366 to Low-E 116 (SHGC: 0.2 / U: 0.25) and revised product and installation quantities. Net increase: $37,414.80. No contractor markup applied. This is the only net new contract value added by this CO.

2.  DOOR AUTOMATION (PREVIOUSLY APPROVED — CO-001) — AutoSlide automatic door operator systems for 3 sliding door openings, per owner selection. Originally approved as CO-001 ($20,038.95) on 2026-02-20. Incorporated herein for completeness; no additional contract value.

3.  RETRACTABLE SCREENS (PREVIOUSLY APPROVED — CO-007 STG) — Retractable screen systems for four (4) sliding door openings: Dining Room, Primary Bedroom, Primary Bathroom, ADU/Casita Sliding Doors. Per Est. #3877, St. George Windows & Doors, Feb. 24, 2026. Passed through at vendor invoice rate as a goodwill gesture; no markup. Originally approved as CO-007 ($23,869.90) on 2026-03-03. Incorporated herein; no additional contract value.

## PART A — Glass Package Price Adjustment (Net New)

Ref: Est. #3692 (Sep. 8, 2025, $237,691.65) vs. Est. #3692 revised (Oct. 30, 2025, $275,106.45) — St. George Windows / Strata Windows & Doors

| Line Item Description | Original | Revised | Delta |
| --- | --- | --- | --- |
| Strata Thermally Broken Aluminum Windows & Doors — Product Supply (Low-E 366 → Low-E 116, SHGC:0.2/U:0.25) | $209,695.15 | $219,474.42 | +$9,779.27 |
| Operable Window Installation (1.63 sq.m @ $110/sq.m) | $179.30 | $179.30 | $0.00 |
| Fixed Window Installation — qty reduction (11.88 → 8.64 sq.m @ $80/sq.m) | $950.40 | $691.20 | -$259.20 |
| Fixed XL Window Installation — qty reduction (8.37 → 1.93 sq.m @ $100/sq.m) | $837.00 | $193.00 | -$644.00 |
| O2B Fixed Window Installation (3.24 sq.m @ $140/sq.m) | $453.60 | $453.60 | $0.00 |
| O2B XL Fixed Window Installation (4.0 sq.m @ $130/sq.m) | $520.00 | $520.00 | $0.00 |
| Fixed Corner Window Installation (4.72 sq.m @ $180/sq.m) | $849.60 | $849.60 | $0.00 |
| Curtain Wall Window Installation (98 sq.m @ $260/sq.m) | $25,480.00 | $25,480.00 | $0.00 |
| 3-Panel Sliding Door Install — 17'x10' (Kitchen) | $1,745.00 | $1,745.00 | $0.00 |
| 3-Panel Sliding Door Install — 14'x10' | $1,695.00 | $1,695.00 | $0.00 |
| 4-Panel Sliding Door Install — 19'x10' | $2,145.00 | $2,145.00 | $0.00 |
| 2-Panel Sliding Door Install — 13'x10' (Casita Bed) | $1,595.00 | $1,595.00 | $0.00 |
| 3-Panel Sliding Door Install — 19'x10' (Casita Living) | $1,895.00 | $1,895.00 | $0.00 |
| 4-Panel + Corner Meet Sliding Door Install — 19'x10' (Primary Suite Bath) | $2,645.00 | $2,645.00 | $0.00 |
| 3-Panel Sliding Door Install — 19'x12' (Primary Suite Bath wide) | $2,045.00 | $2,045.00 | $0.00 |
| Glass Suction Trolley | $2,850.00 | $2,850.00 | $0.00 |
| Forklift Rental | $2,075.00 | $2,075.00 | $0.00 |
| Boom Lift Rental | $2,075.00 | $2,075.00 | $0.00 |
| Window Silicone Sausage (113 units @ $12.95) | $1,463.35 | $1,463.35 | $0.00 |
| 9" x 75' Sticky Window Flashing (15 rolls @ $89.95) | $1,349.25 | $1,349.25 | $0.00 |
| Shipping — Delivery to Hurricane, UT | $27,996.50 | $27,996.50 | $0.00 |
| PART A SUBTOTAL | $237,691.65 | $275,106.45 | +$37,414.80 |

## PART B — Door Automation / AutoSlide (CO-001, Previously Approved)

| Description | Qty | Amount |
| --- | --- | --- |
| AutoSlide Automatic Door Operator Systems — supply and install, 3 sliding door openings per owner selection. Approved 2026-02-20 by Jessica Rodriguez (CO-001). | LS | $20,038.95 |
| PART B SUBTOTAL (previously approved — no new contract value) |  | $20,038.95 |

## PART C — Retractable Screens (CO-007 STG, Previously Approved)

Ref: Estimate #3877 — St. George Windows, Doors & More LLC, Feb. 24, 2026. No markup per goodwill agreement.

| Description | Qty | Amount |
| --- | --- | --- |
| Retractable Screen Systems — 4 openings: Dining Room, Primary Bedroom, Primary Bathroom, ADU/Casita Sliding Doors. Supply and install per Est. #3877. Passed through at vendor invoice rate. Approved 2026-03-03 by Adrian Rodriguez (CO-007). | LS | $23,869.90 |
| PART C SUBTOTAL (previously approved — no new contract value) |  | $23,869.90 |

# CO-001-7 COST SUMMARY

| Part A — Glass Package Price Increase (net new) | $37,414.80 |
| --- | --- |
| Part B — Door Automation (CO-001, previously approved — reference only) | $20,038.95 |
| Part C — Retractable Screens (CO-007, previously approved — reference only) | $23,869.90 |
| Gross Total (including previously approved items) | $81,323.65 |
| Less: Previously Approved (CO-001 + CO-007 STG) | -$43,908.85 |
| Net New Subtotal (glass price increase only) | $37,414.80 |
| Contractor Overhead & Profit — 10% on net new | $0.00 |
| NET NEW AMOUNT THIS CHANGE ORDER (CO-001-7) | $37,414.80 |

# CONTRACT SUM RECONCILIATION

| CO # | Description | Vendor | Amount |
| --- | --- | --- | --- |
| — | Original Contract Sum | RAC Inc. | $3,168,660.00 |
| CO-001 | Glass Door Automation — 3 sliding doors (approved 2026-02-20) — VOIDED, replaced by CO-001-7 | Saint George Glass | $20,038.95 |
| CO-002 | Gun Range Equipment Upgrade — Basic to High End Home Shooting Range Package (approved 2026-02-24) | Action Target Inc. | $42,574.00 |
| CO-003 | Solar Fence Design Modification — panel count 38→31, voltage 650V→705V (approved 2026-02-24) | Cannonball Welding | $0.00 |
| CO-004 | Gun Range/Panic Room HVAC Redesign — remove ceiling cassette mini split, add supply blower, electric heater, evap cooler; high wall units in gun range and panic room (approved 2026-02-25) | RAC Inc. | $0.00 |
| CO-005 | AV Panel & Smart Fixture Upgrade — replace 11 Google Nest panels w/ Axion Android PoE 8" panels; add 5.5" touch panels at single gang locations; smart on/off switches; 2 Leotachi 32x24 smart mirrors; 1 motorized uplift LED medicine cabinet (approved 2026-03-05) — PRICING TBD | RAC Inc. | TBD |
| CO-006 | Hose Bibs & Electrical Additions — 2 frost-free hose bibs at upper level exterior; 2 x 120V 20A duplex outlets in basement panic room (approved 2026-02-26) | RAC Inc. | $0.00 |
| CO-007 (CHE) | Creative Home Engineering Secret Door Security Upgrade — Proposal Rev.1 → Rev.2; enhanced access control, forced entry protection, ballistic resistance on Door 1 (Outer Concrete Tile) and Door 2 (Inner Dry-Stack Stone to Vault); 10% RAC markup on net difference (approved 2026-02-26) | Creative Home Engineering | $26,862.00 |
| CO-007 (STG) | Retractable Screens — 4 openings: Dining Room, Primary Bedroom, Primary Bathroom, ADU/Casita; no markup (approved 2026-03-03) — VOIDED, replaced by CO-001-7 | St. George Windows | $23,869.90 |
|  | Previously Approved CO Total (per system) |  | $113,344.85 |
| CO-001-7 | Glass Package Price Increase + Automation + Screens (net new contract value — glass delta only, no markup) | RAC Inc. | $37,414.80 |
|  | REVISED CONTRACT SUM (excluding CO-005 TBD) |  | $3,319,419.65 |

Note: CO-005 (AV Panel & Smart Fixture Upgrade) has been approved in scope but pricing is to be submitted under separate schedule. Contract sum will be adjusted upon receipt of CO-005 pricing.

# TERMS

1.  This Change Order is incorporated into and subject to the terms of the original Prime Contract between RAC Inc. and ARJR Kanarraville Holdings, LLC dated per original agreement.

2.  CO-001 and CO-007 (St. George Windows) are hereby voided and superseded in their entirety. No separate payments shall be made or demanded under those change orders. All amounts were previously approved and are captured in the approved CO total of $113,344.85.

3.  The net new contract addition from this CO-001-7 is $37,414.80, representing only the glass package price increase. No contractor markup is applied to this change order.

4.  CO-005 pricing remains outstanding and will be addressed in a subsequent change order upon final scope pricing.

5.  All other terms and conditions of the Prime Contract remain in full force and effect.

# SIGNATURES

| CONTRACTOR RAC Inc. Craig Engel, Owner / General Contractor Date | OWNER ARJR Kanarraville Holdings, LLC Authorized Signature Date |
| --- | --- |

RAC Inc.  |  Craig Engel  |  racinc19@gmail.com  |  435-229-7350

Rodriguez Residence — Oak Valley Estates Lot 5, 646 W Liberty Lane, Kanarraville UT 84742