RAC INC.

1267 N 1390 W, St. George, UT 84770  |  435-229-7360  |  racinc19@gmail.com

SUBCONTRACT AGREEMENT

Electrical – Rodriguez Residence, Oak Valley Estates Lot 5

| Contractor | RAC Inc. ¦ Craig Engel ¦ 1267 N 1390 W, St. George, UT 84770 ¦ 435-229-7360 |  |
| --- | --- | --- |
| Subcontractor | Breck Electric Inc. ¦ Breck McArthur ¦ 1130 S 375 E, Ivins, UT 84738 ¦ 435-632-5322 |  |
| Project | Rodriguez Residence – Oak Valley Estates Lot 5 ¦ 646 W Liberty Lane, Kanarraville, UT |  |
| Owner | Jessica and Adrian Rodriguez |  |
| Contract Date | March 3, 2026 | Contract Amount: $68,485.00 |

SCHEDULE OF VALUES

| Item | Description | Amount |
| --- | --- | --- |
| 1 | General Outlets and Power | $22,915.00 |
| 2 | Lighting Wiring and Installation | $15,720.00 |
| 3 | Data Pre-Structure Wiring | $5,250.00 |
| 4 | Low Voltage Wiring (Speakers, Security, AV Equipment, Motorized Blinds) | $9,100.00 |
| 5 | 200 Amp Electrical Service and Panels | $3,100.00 |
| 6 | Installation of Provided Automation Equipment | $2,600.00 |
| 7 | Surface Conduit for Devices in Gun Room | $2,400.00 |
| 8 | Install Exterior Track Lighting (400 LF) | $1,800.00 |
| 9 | Switch Locations – Wiring and Installation of Low Voltage Devices (36 locations) | $3,600.00 |
| 10 | Install Stair Lighting in Rail (40 LF) | $400.00 |
| 11 | Install Lighting in Panic Room Shelves (40 LF) | $400.00 |
| 12 | Install Battery Rack for Solar (4 units) | $1,200.00 |
| TOTAL CONTRACT AMOUNT |  | $68,485.00 |

SUBCONTRACT TERMS AND CONDITIONS

The Subcontractor agrees to the following:

1. Assumption of Responsibilities

Assume all responsibilities and obligations that the Contractor has undertaken for the Owner concerning the subcontract work.

2. Project Timeline

Commence work upon notification by the Contractor and complete the subcontract work within the timeframe necessary for the Contractor to meet its contractual obligations with the Owner. The Subcontractor acknowledges and agrees to be subject to any liquidated damages provisions in the contract with the Owner that result from delays caused by the Subcontractor.

3. Site Cleanup

Maintain a clean worksite by removing all refuse and debris upon completing each unit of work. All excess materials, tools, and structures brought onto the premises by the Subcontractor must be promptly removed. If the Subcontractor fails to do so after reasonable notice, the Contractor may undertake the cleanup at the Subcontractor's expense.

4. Satisfactory Performance

Perform all work to the full satisfaction of both the Contractor and the Owner. If, at any point, the Contractor determines that the Subcontractor is not progressing satisfactorily, the Contractor reserves the right, after reasonable notice, to assume control of the subcontract work.

5. Pricing Adjustments

Pricing may be adjusted to account for material cost fluctuations that exceed the estimated amounts outlined in this contract.

6. Plan Changes

Pricing is subject to change if modifications are made to the project plans. All changes must be agreed upon in writing by both parties prior to execution and shall constitute an extra charge over and above this contract amount.

7. Payment Terms

Payment shall be made as follows: 70% of the total contract amount ($47,939.50) is due upon completion of rough-in inspections; the remaining 30% ($20,545.50) is due upon final completion and sign-off. No retainage will be withheld. Payments will be issued within Net 10 days of each milestone. A late payment fee of $10 per day will apply for up to 15 days; after this period, the Subcontractor will no longer be obligated to complete the project. This contract expressly excludes light fixtures and service trenching costs.

8. Electrical Scope of Work

Subcontractor shall furnish all labor, materials, and equipment necessary to complete the full electrical scope for the Rodriguez Residence per the approved construction documents and the estimate dated 2/26/26, including but not limited to:

- General outlets, circuits, and power distribution throughout all levels

- Lighting wiring and installation

- Data pre-structure wiring

- Low voltage wiring including speakers, security, AV equipment, and motorized blinds

- 200 Amp electrical service and panels

- Installation of owner/contractor-provided automation equipment

- Surface conduit for devices in Gun Room

- Exterior track lighting (400 LF)

- 36 low-voltage switch locations – wiring and device installation

- Stair lighting in rail (40 LF)

- Lighting in Panic Room shelves (40 LF)

- Battery rack installation for solar system (4 units)

- All smoke and carbon monoxide detectors as required by code

- All circuits as required by code and approved plans

9. Exclusions

This contract expressly excludes: specialty and decorative light fixtures (unless specifically requested in writing); service trenching costs; and any work not described in this agreement. All additional or revised work shall be authorized in writing as a change order prior to commencement.

10. Insurance and Licensing

Subcontractor shall maintain all required state and local licenses in good standing for the duration of this project. All workers shall be fully covered by Workers' Compensation Insurance. Proof of insurance shall be provided to Contractor upon request.

ACCEPTANCE OF CONTRACT

The prices, specifications, and conditions stated herein are satisfactory and are hereby accepted. Both parties are authorized to perform the work as specified. Payment will be made as outlined in Section 7 of this agreement.

| RAC Inc. (Contractor) Craig Engel General Contractor Date: ___________________ |  | Breck Electric Inc. (Subcontractor) B Breck McArthur President Date: ___________________ |
| --- | --- | --- |