## To do
[5 empty] | Lot 2, Trumbull - |  | Questions | Drawing
Structural | Rosenberg | krystals@racivil.com |  |  | 435-218-9510 |  | Ceiling/Wall | Manual J&D | emailed
Geo | Gem | brennan@gemenginc.com |  |  |  |  | Niche | Jones
Permit |  |  |  |  | Lot 3, Casey- 435-229-7948 |  |  | Fitures
Survey | [7 empty] | fans
Sign |  |  |  |  | Trumbell Bundy |  | Wall Tile | Switch legs
[5 empty] | 435 218 9510 |  | Vanity mirror | Panel Calcs
Road Prep | Dom Klesch |  | 435-463-8210 | Seth Newtson |  |  | 120 Fixture problems | Switching
Well | Dom Klesch |  |  |  | Todd |  | Wood floor Adu Closet | Topo/Grading
Power | Dom Klesch |  |  |  | 435 705 4264
Gas | Dom Klesch | [5 empty] | .
Septic | Dom Klesch
Internet | Dom Klesch
Temp Facilities
Excavation/Pad Prep/Backfill
Concrete | Randy Frie
Foundatin Wall | Randy Frie
WaterProffing
Termite
Steel | D Iron works
Truss | Sunpro | smitcheel@sunpro.com
Framing Material | Sunroc | smitcheel@sunpro.com
Framing Labor | Elwin | gieframing502@gmail.com
Stair
EXT Doors | Sunpro | srmitchel@sunpro.com
Windows | STG | nathan@lpbuildingsolutions.com
Glass | STG
Roofing
Roof Deck
Roof Metal
Stucco | Simco
Stone | Simco
Rammed Earth | Clayworks | ger@clay-works.com | Allysa Oliver
Rammed Earth Labor | Woodland Stucco | woodlandstuccoandpaint@gmail.com |  | 30 int 40 Ex | Labor only
Mechanical | Dash
Plumbing | Master | office@masterplumbingsystems.com
Gas | Master | office@masterplumbingsystems.com
Plumbing Fixtures
Electrical | Dash
Electrical Fixtures
Solar
Solar Material
Fireplace
Insulation | LP | nathan@lpbuildingsolutions.com
Drywall | H&E | hedrywall1022@gmail.com | 5.7 | House | Gawal
Plaster | Simco |  | 5.5 | Stucco
Paint | Jose | woodlandstuccoandpaint@gmail.com | 3.3 | House
Garage Door | Sunroc | srmitchel@sunpro.com
Flooring Material | G&S
Flooring labor | G&S |  |  |  |  | Doors | 30
Int Doors | Sunroc
Hidden door
Vault Door
Base | Sunroc
Hardware | Sunroc | srmitchel@sunpro.com
Carpentry | A&L | ammon@a&lfinish
Cabinet | Deez | deezcabnuts@gmail.com | rrcabinetsinc@gmail.com
Closet
Tile Material
Tile Labor | G&S
Floor Heat
Steam
Clayworks
Countertop | Countertop Source
Bath Hardware
Mirrors & Specialty Glass
Appliance | Boulevard | haley.benware@blvdhome.com
AV
Range | Chris | chrishr@actiontarget.com
Railing |  | Broken Horn
Landscape/Drive
Pavers

## Budget1
Who is it Yes I meet that bunch of real cast like you know you got to watch you I this guy Got fucking indigestion from the sugar Yep Well yeah I feel like I know I've stabbed you you It's not too long that's just not fair to me Oh Whoops | 646 W Liberty Lane | -7255.149 | AKA 1025 S | Kannerrville | 84742
10%
Sq Ft | 6993 | Budget | Budget | CPF | Duration | Completion | Pay Schedule | Profit
Build Gross | 2846193.361 | 2853448.51 | 3088193.361 | 363.6699 | 383 | 2026-04-15 | 3089193.361 | -234744.851
Deposit | 545050 | [7 empty] | 603350 | Cost to permit/deposit
Plumbing Fixtures | RAC | 17000 | 18700 | 2.6741 |  | 2025-02-01 |  |  | 242000 | 2025-11-30
Electrical Fixtures | RAC | 18000 | 19800 | 2.8314 |  | 2025-02-01 |  |  |  | 2025-12-30
Hidden Door |  | 25000 | 27500 | 3.9325 |  | 2025-02-01 |  |  | 1000 | 2026-01-30
Vault Door |  | 7500 | 8250 | 1.1798 |  | 2025-02-01 |  |  |  | 2026-02-28
Cabinet | Deez | 26000 | 28600 | 4.0898 |  | 2025-02-01 |  |  | 187660 | 2026-03-30
Entry Stair | TGC | 17000 | 18700 | 2.6741 |  | 2025-02-01 |  |  | 262900 | 2026-04-30
Tile Material | RAC | 80000 | 88000 | 12.584 |  | 2025-02-01 |  |  | 415800 | 2026-05-30
Rammed Earth | Alysa Oliver | 50000 | 55000 | 7.865 |  | 2025-02-01 |  |  | 78650 | 2026-06-30
Exterior Glass | STG | 115000 | 126500 | 18.0895 |  | 2025-02-01 |  |  | 296450 | 2026-07-30
Rammed earth Material | Clayworks | 45000 | 49500 | 7.0785 |  | 2025-02-01 |  |  | 243100 | 2026-08-30
Railing |  | 46000
Range | Action Target | 95000 | 104500 | 14.9435 |  | 2025-02-01 |  |  | 287650 | 2026-09-30
Permiting | 58300 | [7 empty] | 27500 | 2026-10-30
Facilities |  | 10000 | 11000 | 1.573 |  | 2025-02-01 |  |  | 30800 | 2026-11-30
Permits | Iron County | 30000 | 33000 | 4.719 |  | 2025-02-02 |  | Total | 2676860
Builders Risk |  | 5000 | 5500 | 0.7865 |  | 2025-02-03
Manual J |  | 1500 | 1650 | 0.23595 |  | 2025-02-04
Plans | Steamroller | 1000 | 1100 | 0.1573 |  | 2025-02-05 |  |  | 2181
Soil | Gem | 3000 | 3300 | 0.4719 |  | 2025-02-06 |  |  | 409
Inspections |  | 2500 | 2750 | 0.39325 |  | 2025-02-07 | 603350 |  | 2206
Site Utilities | All right | [7 empty] | 919
Site Utilities |  | 122000 | 134200 | 19.1906 | 7 | 2025-02-18 |  |  | 1278
Road |  | 78000 | 85800 | 12.2694 | 14 | 2025-03-10
Gas | RAC | 10000 | 11000 | 1.573 | 2 | 2025-03-12
Power |  | 5000 | 5500 | 0.7865 | 5 | 2025-03-19 |  |  | 1979
Water |  | 5000 | 5500 | 0.7865 | 4 | 2025-03-25 | 242000 |  | 3229
Structural | 599993.361 | [7 empty] | 5208 | 31.2596
Ftgs | Frie | 35710.41 | 39281.451 | 5.6173 | 7 | 2025-04-03
Wall | Frie | 63078 | 69385.8 | 9.9222 | 7 | 2025-04-14
Slab | Frie | 49345.1 | 54279.61 | 7.762 | 7 | 2025-04-23
Pan | Frie | 32075 | 35282.5 | 5.0454 | 7 | 2025-05-02
Site | Frie | 9640 | 10604 | 1.5164 | 7 | 2025-05-13 | 208833.361
Pretreat | RAC | 1000 | 1100 | 0.1573 | 7 | 2025-05-13 | 1000
Steel | D-Iron Works | 184000 | 202400 | 28.9432 | 27 | 2025-06-19 | 184000
Lumber | Sunpro | 50000 | 55000 | 7.865 |  | 2025-06-19
Framing Labor | DAG | 80600 | 88660 | 12.6784 | 27 | 2025-07-28
Truss | SunPro | 40000 | 44000 | 6.292 |  | 2025-07-28 | 187660
Mechanical Rough | 252450
HVAC/ERV | Dash | 32000 | 35200 | 5.0336 | 5 | 2025-08-04
Plumbing/Gas | Master | 25000 | 27500 | 3.9325 | 5 | 2025-08-11
Electrical | DAsh | 45000 | 49500 | 7.0785 | 10 | 2025-08-25
AV | Tek it | 80000 | 88000 | 12.584 | 5 | 2025-09-01
Solar | Raven | 25000 | 27500 | 3.9325 |  | 2025-09-01
Fireplace | Master | 22500 | 24750 | 3.5393 | 1 | 2025-09-02
Exterior Sealing | 470250
Roofing | RAC | 35000 | 38500 | 5.5055 | 7 | 2025-08-06
Coatings | Advance | 102000 | 112200 | 16.0446 | 14 | 2025-08-26 | 262900
Exterior Glass | STG | 115000 | 126500 | 18.0895 | 14 | 2025-09-15
Exterior Doors | Sunroc | 13000 | 14300 | 2.0449 | 2 | 2025-09-17
Garage Door | Sunroc | 22500 | 24750 | 3.5393 | 5 | 2025-09-24
Exterior Stucco | Simco | 60000 | 66000 | 9.438 |  | 2025-09-24
Stone Veneer | Simco | 30000 | 33000 | 4.719 | 5 | 2025-10-01
Rammed Earth | Alysa Oliver | 50000 | 55000 | 7.865 | 21 | 2025-10-30
Wall/Cieling Finish | 173250
Insulation | LP | 40000 | 44000 | 6.292 | 2 | 2025-09-04 | 415800
Sheetrock | H&E | 41500 | 45650 | 6.528 | 28 | 2025-10-14 | 78650
Paint | Jose | 23000 | 25300 | 3.6179 | 14 | 2025-11-03
Tile Labor | GS | 53000 | 58300 | 8.3369 |  | 2025-11-03
Carpentery | 204600
Cabinet | Deez | 26000 | 28600 | 4.0898 | 3 | 2025-11-06
Countertops | Countertop source | 45000 | 49500 | 7.0785 | 1 | 2025-11-07
Finish Carpentry | A&L | 12000 | 13200 | 1.8876 | 5 | 2025-11-14
Door | Sunpro | 28500 | 31350 | 4.4831 | 5 | 2025-11-21
Base&Case | Sunpro | 5000 | 5500 | 0.7865 |  | 2025-11-21
Door & Bath Hardware | Sunpro | 5000 | 5500 | 0.7865 | 2 | 2025-11-25
Entry Stair | TGC | 17000 | 18700 | 2.6741 |  | 2025-11-25
Wood Stair | RAC | 5000 | 5500 | 0.7865 | 2 | 2025-11-27 | 296450
Stair Labor | RAC | 10000 | 11000 | 1.573 | 2 | 2025-12-01
Vault Door | RAC | 7500 | 8250 | 1.1798 | 2 | 2025-12-03
Hidden Door |  | 25000 | 27500 | 3.9325 | 2 | 2025-12-05
Equipment/ Finishes | 484000
HVAC/ERV |  | 21500 | 23650 | 3.382 | 3 | 2025-12-10
Plumbing/Gas | Master | 32000 | 35200 | 5.0336 | 3 | 2025-12-15
Electrical | RAC | 45000 | 49500 | 7.0785 | 3 | 2025-12-18
AV | Tek it | 80000 | 88000 | 12.584 | 5 | 2025-12-25 | 243100
Range | Action Target | 95000 | 104500 | 14.9435 | 7 | 2026-01-05
Appliance | Blvd | 48000 | 52800 | 7.5504 | 1 | 2026-01-06
Glass | RAC | 7500 | 8250 | 1.1798 | 2 | 2026-01-08
Railing | Broken Horn | 46000 | 50600 | 7.2358 | 5 | 2026-01-15
Outdoor | RAC | 60000 | 66000 | 9.438 | 5 | 2026-01-22
Cleaning | RAC | 5000 | 5500 | 0.7865 | 3 | 2026-01-27 | 287650
Landscape | 58300 |  |  |  |  | `
Solar | Raven | 25000 | 27500 | 3.9325 | 4 | 2026-02-02 | 27500
Landscape | RAC |  | 0 | 0 | 21 | 2026-03-03
Pavers | RAC | 28000 | 30800 | 4.4044 | 10 | 2026-03-17 | 30800
Contingency |  |  |  | 0 | 21 | 2026-04-15
Options | [5 empty] | 2026-04-15
Steam | RAC | [5 empty] | 12000
Floor Heat | RAC | [5 empty] | 7500

## Sheet29
ex | Supply Prropne tank
spec waterr collection tank
include water pipe to collection
spec waterr collection tank
well tie in need add

## Fixtures
That's it |  |  |  |  | Flooring |  |  |  | Electircal Fixtures | Flooring/Tile | AV | Solar
Sinks |  |  |  |  | Paver | 2470 | 11 | 27170
Glacier Bay 33 | 2 | 300 | Kitchen |  | Pergo | 1172 | 3 | 3516
Horrow Undermount |  | 120 | ADU |  | Nashville | 2636 | 9 | 23724
Horrow Undermount |  | 120 | Powder |  | Carpet | 950 | 3 | 2850
Horrow Undermount |  | 120 | Office |  | Carra | 783 | 9 | 7047
Horrow Undermount |  | 120 | ADU |  | Wall Tile | 755 | 20 | 15100
Horrow Undermount |  | 240 | Primary |  | concrete Tile | 600 | 20 | 12000
Mop Sink |  | 319 |  | Wand?
Faucet |  |  |  |  | Total |  |  | 91407
Kohler Crue Touchless | 2 | 900 | Kitchen
Arc Waterfall |  | 50 | ADU |  | Labor Floor | 4591 | 6 | 27546
Arc Waterfall |  | 50 | Powder |  | Labor Wall | 1355 | 16 | 21680
Arc Waterfall |  | 50 | Office |  | Carpet | 950 | 3 | 2850
Arc Waterfall |  | 50 | ADU
Arc Waterfall |  | 100 | Primary |  | total |  |  | 52076
Moen Wall Mount |  | 140 | Garage
Toilet
Horrow Unique | 6 | 6000
Shower Valve
Granjoy | 3 | 3000
Tub |  | 3500
Tub Filler |  | 1000
Drains
Oatey 24" Linear | 3 | 375
Total |  | 16554

## Appliance
Kitchen
Appliance site | http://www.thermador.com/
36" Refridge Column | https://www.thermador.com/us/en/mkt-product/refrigeration/refrigerationrefrigerationcolumns/T36IR905SP
36" Freezer Column | https://www.thermador.com/us/en/mkt-product/refrigeration/freezer-columns/T36IF905SP
Double Oven | https://www.thermador.com/us/en/mkt-product/ovens/double-ovens/MEDMC301WS
Dishwasher | https://www.thermador.com/us/en/mkt-product/dishwashers/custom-panel/DWHD640EPR
Hood | https://futurofuturo.com/54-skylight-ceiling-soffit-range-hood/?gad_source=1&gad_campaignid=22020168852&gbraid=0AAAAAD_hDAqqlhc5Adnrl7h_avAB-_94G&gclid=Cj0KCQjwxJvBBhDuARIsAGUgNfjVKi_F2Q8pLZHI8rJNJsrPAnkCamTcDZ1jcF-O4WFol61rn8Fug2caAnlzEALw_wcB
Cooktop | https://www.infinitysurfaces.it/invisible-induction-cooktop/
Under Counter Fridge | https://www.homedepot.com/p/TITTLA-24-in-Single-Zone-150-Can-Beverage-Refrigerator-in-Silver-with-2-Different-Door-Handles-Built-in-Beverage-Cooler-KMBR150/326580232
Ice maker 400 | https://www.homedepot.com/p/TITTLA-14-in-100-lbs-Full-Size-Ice-Cubes-per-day-Ice-Maker-with-Blue-LEDs-Interior-in-Silver-Stainless-Steel-HY45FT/326504176
Ice maker 900 | https://www.homedepot.com/p/COTLIN-15-in-22-lb-Built-In-Ice-Maker-in-Stainless-Steel-with-Reversible-Door-Crescent-Ice-IMC25BI/328501726
ADU
Package | https://www.homedepot.com/p/sets/Frigidaire-25-6-cu-ft-Standard-Depth-Refrigerator-with-5-Burner-Freestanding-Electric-Range-and-Dishwasher/335525148
Stack | recomend
Laundry | recomend
Washer | recomend

## Load
What the fuck did I do with this shit man | Calculated Load (A) | Continuous Load x 125% | Recommended Breaker | Recommended Conductor (Cu) | Recommended Conduit |  |  |  |  | Amps
Panel 1 | 239 | 298.8 | 300 A | 350 kcmil x 3 conductors + #2 AWG Ground | 2.5" EMT (minimum)
Panel 2 | 250.5 | 313.1 | 300 A | 350 kcmil x 3 conductors + #2 AWG Ground | 2.5" EMT (minimum)
Panel 3 | 179.3 | 224.1 | 225 A | 4/0 AWG x 3 conductors + #4 AWG Ground | 2" EMT (minimum)
Main Transformer | 668.8 | 836 | 800 A Main | Parallel 500 kcmil x 4 per phase + 1/0 Ground | Dual 3" EMT runs (per phase)
**TOTAL PANEL 1 LOAD**
Lighting Loads | Load | Feet/Location | Watts | Load A | Transformer | Breaker | NCL A
Total |  |  | 3228.9 | 127.3375 |  |  | 127.335
Circuit 1 | P1-EXT-1 |  | 160.02 | 6.6675 | HDR-240-24 (10A) | 7A | 6.67 | ShellY RGBWW Pro | Dimmer
Circuit 2 | P1-EXT-2 |  | 297.18 | 12.3825 | HDR-480-24 (20A) | 15 A | 12.38 | ShellY RGBWW Pro | Dimmer
Circuit 3 | P1-EXT-3 |  | 228.6 | 9.525 | HDR-320-24 (13.3A) | 10A | 9.53 | ShellY RGBWW Pro | Dimmer
Circuit 4 | P1-EXT-4 |  | 388.62 | 16.1925 | HDR-480-24 (20A) | 20 A | 16.19 | ShellY RGBWW Pro | Dimmer
Circuit 5 | P1-EXT-5 |  | 274.32 | 11.43 | HDR-320-24 (13.3A) | 15 A | 11.43 | ShellY RGBWW Pro | Dimmer
Circuit 6 | P1-EXT-6 |  | 320.04 | 13.335 | HDR-480-24 (20A) | 15 A | 13.33 | ShellY RGBWW Pro | Dimmer
Circuit 7 | P1-EXT-7 |  | 274.32 | 11.43 | HDR-320-24 (13.3A) | 15 A | 11.43 | ShellY RGBWW Pro | Dimmer
Circuit 8 | P1-LVC-1 | Kitchen Cooktop | 168 | 7 | HDR-320-24 (13.3A) | 15 A | 7 | ShellY RGBWW Pro | Dimmer
Circuit 1 | P1-LVC-2 | Kitchen dish Sink | 72 | 3 | HDR-150-24 (5A) | 7A | 3 | ShellY RGBWW Pro | Dimmer
Circuit 9 | P1-LVC-3 | Office | 360 | 15 | HDR-480-24 (20A) | 15 A | 15 | ShellY RGBWW Pro | Dimmer
Circuit 10 | P1-LVM-1 | Garge | 36 | 1.5 | HDR-320-24 (20A) | 15 A | 12 | Shelly 1 PM
| P1-LVM-2 | Systems Garage | 18 | 0.75 | Combined 24V-10 |  |  | Shelly 1 PM
| P1-LVM-3 | Back Stair | 36 | 1.5 | Combined 24V-10 |  |  | tx | Dimmer
| P1-LVM-4 | Mechanical | 18 | 0.75 | Combined 24V-10 |  |  | Shelly 1 PM
| P1-LVM-5 | Storage | 18 | 0.75 | Combined 24V-10 |  |  | Shelly 1 PM
| P1-LVM-6 | Pantry | 54 | 2.25 | Combined 24V-10 |  |  | Shelly 1 PM
| P1-LVM-7 | Office Closet | 36 | 1.5 | Combined 24V-10 |  |  | Shelly 1 PM
| P1-LB-8 | Office Bath | 72 | 3 | Combined 24V-10 |  |  | Shelly 2 PM Pro-1.1 | Dimmer
Circuit 11 | P1-L120-1 | Powder | 75 | 3.125 | HDR-480-24 (20A) | 15 A | 9.375 | Shelly 1 PM
| P1-L120-2 | Island | 75 | 3.125 | Combined 120V-11 |  |  | Shelly 2 PM Pro-1.1 | Dimmer
| P1-L120-3 | Dining | 75 | 3.125 | Combined 120V-11 |  |  | Shelly 2 PM Pro-1.1 | Dimmer
Wall Loads
Total |  |  |  | 231.44 |  |  | 294.44
Circuit 12 | P1-120-1 (120V) |  |  | 16 | 120V Circuit | 40 A GFCI | 16 | Shelly PM-4-1.1
| P1-120-2 (120V) |  |  | 16 | 120V Circuit |  | 16 | Shelly PM-4-1.2
| P1-120-3 (120V) |  |  | 16 | 120V Circuit |  | 16 | Shelly PM-4-1.3
| P1-120-4 (120V) |  |  | 16 | 120V Circuit |  | 16 | Shelly PM-4-1.4
| P1-120-5 (120V) |  |  | 16 | 120V Circuit | 40 A GFCI | 16 | Shelly PM-4-2.1
| P1-120-6 (120V) | [5 empty] | 16 | Shelly PM-4-2.2
| P1-120-7 (120V) | [5 empty] | 16 | Shelly PM-4-2.3
| P1-120-8 (120V) | [5 empty] | 16 | Shelly PM-4-2.4
| P1-120-9 (120V) |  |  |  |  | 15 | 15 | Shelly 1 PM
Circuit 13 | 220-1 (220V) |  |  | 16 | 220V Circuit | 40 A GFCI | 16 | Shelly PM-4-3.1
| 220-2 (220V) |  |  | 16 | 220V Circuit |  | 16 | Shelly PM-4-3.2
| 220-3 (220V) |  |  | 16 | 220V Circuit |  | 16 | Shelly PM-4-3.3
| 220-4 (220V) |  |  | 16 | 220V Circuit |  | 16 | Shelly PM-4-3.4
Circuit 14 | 220-5 (220V) |  |  | 16 | 220V Circuit | 15A | 16 | Shelly 1 PM
Circuit 15 | 220-6 (220V) |  |  | 30 | 220V Circuit | 30 A | 30
Circuit 16 | 220-7 (220V) |  |  | 40 | 220V Circuit | 40 A | 40
Blinds
Circuit 3 | Lower West 1 |  | 57.6 | 0.48 | 120V Circuit |  | 1.44 | Shelly Dual Cover 1.1
| Lower West 2 |  | 115.2 | 0.96 | Combined 120V-3 |  |  | Shelly Dual Cover 1.2
**TOTAL PANEL 2 LOAD** |  |  | 4071.02 | 161.2258 | Total |  | 176.5467
Lighting Loads | Load | Feet/Location | Watts | Continuous A | Transformer | Breaker | NCL A
Total |  |  | 2035.51 | 80.6129 |  |  | 88.2733
Circuit 1 | P2-EXT1 | 20 | 91.35 | 3.8062 | HDR-240-24 (10A) | 5A | 3.81 | ShellY RGBWW Pro | Dimmer
| P2-EXT2 | 35 | 159.86 | 6.6608 | HDR-240-24 (10A) | 8A | 6.66 | ShellY RGBWW Pro | Dimmer
Circuit 2 | P2-EXT3 | 16 | 73.08 | 3.045 | HDR-240-24 (10A) | 5A | 3.04 | ShellY RGBWW Pro | Dimmer
| P2-EXT4 | 40 | 182.7 | 7.6125 | HDR-240-24 (10A) | 10A | 7.61 | ShellY RGBWW Pro | Dimmer
Circuit 3 | P2-EXT5 | 70 | 319.72 | 13.3217 | HDR-320-24 (13.3A) | 15 A | 13.32 | ShellY RGBWW Pro | Dimmer
Circuit 4 | P2-LVC-1 |  | 216 | 9 | HDR-320-24 (13.3A) | 12A | 9 | ShellY RGBWW Pro | Dimmer
Circuit 5 | P2-LVC-2 |  | 240 | 10 | HDR-320-24 (13.3A) | 15 A | 10 | ShellY RGBWW Pro | Dimmer
Circuit 6 | P2-LVC-3 |  | 240 | 10 | HDR-320-24 (13.3A) | 16 A | 10 | ShellY RGBWW Pro | Dimmer
Circuit 7 | P2-LVM-1 | Mechanical | 18 | 0.75 | HDR-480-24 (20A) | 40 | 17.1667 | Shelly PM-4-1.1
| P2-LVM-2 | Closet | 48 | 2 | Combined 24V-7 |  |  | Shelly PM-4-1.2
| P2-LVM-4 | Garage | 36 | 1.5 | Combined 24V-7 |  |  | Shelly PM-4-1.3
| P2-LVM-5 | Garage | 126 | 5.25 | Combined 24V-7 |  |  | Shelly PM-4-1.4
Circuit 8 | P2-LVM-3 | Bath | 72 | 3 | HDR-150-24 | 10A | 7.6667 | Shelly 2 PM Pro-1.1 | Dimmer |  |  | 72 | 3 | Combined 24V-7
| P2-FL-120-1 |  | 40 | 1.6667 | 120V Circuit |  |  | Shelly 2 PM Pro-1.1 | Dimmer
| P2-F-120-1 |  |  | 1 | 120V Circuit |  |  | Shelly PM-1
| P2-FL-120-2 |  |  | 1 | 120V Circuit |  |  | Shelly 2 PM Pro-1.1 | Dimmer
| P2-F-120-2 |  |  | 1 | 120V Circuit |  |  | Shelly PM-1
Wall Loads
|  |  |  | 315.4 |  |  | 183.44
| P1-120-1 |  |  | 20 | 120V Circuit |  |  | Shelly PM-4-2.4
Circuit 8 | P1-120-2 |  |  | 20 | 120V Circuit | 40 A GFCI | 16 | Shelly PM-4-3.1
| P1-120-3 |  |  | 20 | 120V Circuit |  | 16 | Shelly PM-4-3.2
| P1-120-4 |  |  | 20 | 120V Circuit |  | 16 | Shelly PM-4-3.3
| P1-120-5 |  |  | 20 | 120V Circuit |  | 16 | Shelly PM-4-3.4
Circuit 9 | P1-120-6 |  |  | 20 | 120V Circuit | 15 | 16 | Shelly PM-1
| 220-1 (220V) |  |  | 20 | 220V Circuit | 40A | 16 | Shelly PM-4 4.1
| 220-2 (220V) |  |  | 20 | 220V Circuit |  | 16 | Shelly PM-4 4.2
Circuit 10 | 220-3 (220V) |  |  | 20 | 220V Circuit |  |  | Shelly PM-4 4.3
Shelly PM-4 4.4
Circuit 11 | 220-4 (220V) |  |  | 30 | 220V Circuit | 30A | 30
Circuit 12 | 220-4 (220V) |  |  | 40 | 220V Circuit | 40A | 40
Blinds
Circuit 4 | Glass East |  | 57.6 | 0.48 | 120V Circuit |  | 0.96 | Shelly Dual Cover 1.1
| West Glass 2-1 |  | 57.6 | 0.48 | 120V Circuit |  |  | Shelly Dual Cover 1.2
| West Glass 2-2 |  | 57.6 | 0.48 | 120V Circuit |  | 0.48 | Shelly Dual Cover 2.1
**TOTAL PANEL 3 LOAD** |  |  | 24V | 83.96 | Total | 179
Lighting Loads | Circuit | Feet | Watts | Amps | Recommended Transformer | Breaker
|  |  | 2747.36 | 198.8733 |  |  | 93.7483
Circuit 1 | P3-EXT-1 | 35 | 160.01 | 6.6671 | HDR-240-24 (10A) | 10A | 6.6671 | ShellY RGBWW Pro | Dimmer
Circuit 2 | P3-EXT-2 | 15 | 68.58 | 2.8575 | HDR-240-24 (10A) | 3.6 A | 2.8575 | ShellY RGBWW Pro | Dimmer
Circuit 3 | P3-EXT-3 | 45 | 205.73 | 8.5721 | HDR-240-24 (10A) | 10.7 A | 8.5721 | ShellY RGBWW Pro | Dimmer
Circuit 4 | P3-EXT-4 | 65 | 297.17 | 12.3821 | HDR-320-24 (13.3A) | 15.5 A | 12.3821 | ShellY RGBWW Pro | Dimmer
Circuit 5 | P3-EXT-5 | 40 | 182.87 | 7.6196 | HDR-240-24 (10A) | 9.5 A | 7.6196 | ShellY RGBWW Pro | Dimmer
Circuit 6 | P3-LVC-1 | Living | 360 | 15 | HDR-480-24 (20A) | 20 A | 15 | ShellY RGBWW Pro | Dimmer
Circuit 7 | P3-LVC-2 | Shower | 120 | 5 | HDR-240-24 (10A) | 7A | 5 | ShellY RGBWW Pro | Dimmer
Circuit 8 | P3-LVC-3 | Bath | 168 | 7 | HDR-320-24 (13.3A) | 10A | 7 | ShellY RGBWW Pro | Dimmer
Circuit 9 | P3-LVC-4 | Master | 312 | 13 | HDR-480-24 (20A) | 15 A | 13 | ShellY RGBWW Pro | Dimmer
Circuit 10 | P3-LVM-1 | Laundry | 18 | 0.75 | HDR-480-24 (20A) | 16 A | 3 | Shelly PM-4-1.1
| P3-LVM-2 | Mechanical | 18 | 0.75 | Combined 24V-10 |  |  | Shelly PM-4-1.2
| P3-LVM-3 | WC-1 | 18 | 0.75 | Combined 24V-10 |  |  | Shelly PM-4-1.3
| P3-LVM-4 | WC-2 | 18 | 0.75 | Combined 24V-10 |  |  | Shelly PM-4-1.4
| P3-LVD-1 | Closet | 288 | 12 | Combined 24V-10
Circuit 11 | P3-120-1 | Entry | 75 | 3.125 | HDR-480-24 (20A) | 20 A | 12.65 | Shelly PM-4-2.1 | [7 empty] | Shelly 2 PM Pro-1 | Dimmer
| P3-120-2 | Foyer | 75 | 3.125 | Combined 24V-11 |  |  | Shelly PM-4-2.2
| P3-120-3 |  | 75 | 3.125 | Combined 24V-11 |  |  | Shelly PM-4-2.3
| P3-Fl-1 |  |  | 1 | Combined 120V-11 |  |  | Shelly PM-4-2.4
| P3-F-1 |  |  | 1 | Combined 120V-11 |  |  | Shelly 2 PM Pro-1.1 | Dimmer
| P3-Fl-2 |  |  | 1 | Combined 120V-11 |  |  | Shelly PM-1
| P3-F-2 |  |  | 1 | Combined 120V-11 |  |  | Shelly 2 PM Pro-1.2 | Dimmer
Wall Loads
Circuit 12 | P1-120-1 (120V) |  |  | 20 | 120V Circuit | 40 A | 16 | Shelly PM-3-3.1
| P2-120-1 (120V) |  |  | 20 | 120V Circuit | 20 A | 16 | Shelly PM-3-3.2
| P3-120-1 (120V) |  |  | 20 | 120V Circuit | 20 A | 16 | Shelly PM-3-3.3
[7 empty] | 16 | Shelly PM-3-3.4
| 220-1 (220V) |  |  | 15 | 220V Circuit | 20 A | 16 | Shelly PM-2-2.1
| 220-2 (220V) |  |  | 15 | 220V Circuit | 20 A | 16 | Shelly PM-2-2.2
Blinds
Circuit 11 | Entry |  | 57.6 | 0.48 | 120V Circuit |  | 0.48 | Shelly Dual Cover 1.1
| Entry 2 |  | 57.6 | 0.48 | 120V Circuit |  | 0.48 | Shelly Dual Cover 1.2
| West Glass Upper 1 |  | 57.6 | 0.48 | 120V Circuit |  | 0.48 | Shelly Dual Cover 2.1
| West Glass Upper 2 |  | 57.6 | 0.48 | 120V Circuit |  | 0.48 | Shelly Dual Cover 2.2
| Glass South |  | 57.6 | 0.48 | 120V Circuit |  | 0.48 | Shelly Dual Cover 3.1
**TOTAL PANEL 4 LOAD**
Lighting Loads | Circuit | Feet | Watts | Amps | Recommended Transformer | Breaker
Circuit 1 | P4-LVS-1 | 40 | 182.8 | 7.6167 | HDR-240-24 (10A) | 10 A | 7.6167 | Shelly 2 PM Pro-1.1 | Dimmer
Circuit 2 | P4-LVS-2 | 40 | 182.8 | 7.6167 | HDR-240-24 (10A) | 10 A | 7.6167 | Shelly 2 PM Pro-1.2 | Dimmer
Circuit 3 | P4-LVS-3 | 65 | 297 | 12.375 | HDR-320-24 (13.3A) | 15 A | 12.375 | Shelly PM-1
Circuit 4 | P4-LVC-1 | Overhead Cans | 360 | 15 | HDR-480-24 (20A) | 20 A | 15 | ShellY RGBWW Pro | Dimmer
Circuit 5 | P4-LVM-1 | Mechanical | 18 | 0.75 | HDR-150-24 (6.3A) | 3.25 | 2.5 | Shelly PM-4-1.1
| P4-LVM-2 | Bath | 24 | 1 | Combined 24V-5 |  |  | Shelly PM-4-1.2
| P4-LVM-3 | Escape 1 | 18 | 0.75 | Combined 24V-6 |  |  | Shelly PM-4-1.3
| P4-LVM-4 | Escape 2 | 18 | 0.75 | Combined 24V-7 |  |  | Shelly PM-4-1.4
Wall Loads
Circuit 6 | P4-1 |  |  | 20 | 120V Circuit | 15 A | 16 | Shelly PM-2-2.1
Circuit 7 | P4-2 |  |  | 20 | 120V Circuit | 15 A | 16 | Shelly PM-2-2.2
Circuit 8 | 220-1 (220V) |  |  | 16 | 220V Circuit | 15 A | 16 | Shelly PM-2-2.1
Circuit 9 | 220-1 (220V) |  |  | 16 | 220V Circuit | 15 A | 16 | Shelly PM-2-2.2
Circuit 10 | 220-2 (220V) |  |  | 30 | 220V Circuit | 30 A | 30
Opening | Width (in) | Height (in) | Tube Size | Motor | Torque (LF) | Torque (BO) | Motor Amps (A) | Watts per Motor | Roll Ø Sheer (in) | Roll Ø Blackout (in) | Recommended Pocket Depth (in) | Power | Control | Fabric | Cumulative Amps (A) | Cumulative Watts | Recommended Breaker | Shelly Pro Dual Required | Shelly Device Channel
Entry | 159 | 268.5 | 100 mm | Somfy Sonesse 100 RS485 | ≥ 15 Nm | ≥ 20 Nm | 0.48 | 57.6 | 4.72 | 5.51 | 8 | 120 VAC | Somfy RS485 Bus → LAN/Homey | Dual Roller Recommended | 0.48 | 57.6 | 15A (OK) | 1 | Ch1
Entry 2 | 96 | 268.5 | 100 mm | Somfy Sonesse 100 RS485 | ≥ 15 Nm | ≥ 20 Nm | 0.48 | 57.6 | 4.72 | 5.51 | 8 | 120 VAC | Somfy RS485 Bus → LAN/Homey | Dual Roller Recommended | 0.96 | 115.2 | 15A (OK) | 1 | Ch2
West Glass 1 | 268 | 314.5 | 100 mm | Somfy Sonesse 100 RS485 Hi-Torque | ≥ 25 Nm | ≥ 35 Nm | 0.48 | 57.6 | 4.84 | 5.73 | 10 | 120 VAC | Somfy RS485 Bus → LAN/Homey | Dual Roller Recommended | 1.44 | 172.8 | 15A (OK) | 2 | Ch1
West Glass Lower 1 | 120 | 207 | 100 mm | Somfy Sonesse 100 RS485 | ≥ 15 Nm | ≥ 20 Nm | 0.48 | 57.6 | 4.55 | 5.19 | 8 | 120 VAC | Somfy RS485 Bus → LAN/Homey | Dual Roller Recommended | 1.92 | 230.4 | 15A (OK) | 2 | Ch2
West Glass Lower 2 | 120 | 209.75 | 100 mm | Somfy Sonesse 100 RS485 | ≥ 15 Nm | ≥ 20 Nm | 0.48 | 57.6 | 4.56 | 5.2 | 8 | 120 VAC | Somfy RS485 Bus → LAN/Homey | Dual Roller Recommended | 2.4 | 288 | 15A (OK) | 3 | Ch1
West Glass Upper 1 | 144 | 236.75 | 100 mm | Somfy Sonesse 100 RS485 | ≥ 15 Nm | ≥ 20 Nm | 0.48 | 57.6 | 4.63 | 5.35 | 8 | 120 VAC | Somfy RS485 Bus → LAN/Homey | Dual Roller Recommended | 2.88 | 345.6 | 15A (OK) | 3 | Ch2
West Glass Upper 2 | 120 | 110.5 | 60 mm | Somfy Sonesse 60 RS485 | ≥ 6 Nm | ≥ 9 Nm | 0.35 | 42 | 2.89 | 3.42 | 6 | 120 VAC | Somfy RS485 Bus → LAN/Homey | Single Roller OK | 3.23 | 387.6 | 15A (OK) | 4 | Ch1
West Glass 2-1 | 120 | 161.5 | 60 mm | Somfy Sonesse 60 RS485 | ≥ 6 Nm | ≥ 9 Nm | 0.35 | 42 | 3.1 | 3.8 | 6 | 120 VAC | Somfy RS485 Bus → LAN/Homey | Dual Roller Recommended | 3.58 | 429.6 | 15A (OK) | 4 | Ch2
West Glass 2-2 | 120 | 228.5 | 100 mm | Somfy Sonesse 100 RS485 | ≥ 15 Nm | ≥ 20 Nm | 0.48 | 57.6 | 4.61 | 5.3 | 8 | 120 VAC | Somfy RS485 Bus → LAN/Homey | Dual Roller Recommended | 4.06 | 487.2 | 15A (OK) | 5 | Ch1
Glass South | 91 | 113.25 | 60 mm | Somfy Sonesse 60 RS485 | ≥ 6 Nm | ≥ 9 Nm | 0.35 | 42 | 2.9 | 3.44 | 6 | 120 VAC | Somfy RS485 Bus → LAN/Homey | Single Roller OK | 4.41 | 529.2 | 15A (OK) | 5 | Ch2
Glass East | 119 | 234 | 100 mm | Somfy Sonesse 100 RS485 | ≥ 15 Nm | ≥ 20 Nm | 0.48 | 57.6 | 4.62 | 5.33 | 8 | 120 VAC | Somfy RS485 Bus → LAN/Homey | Dual Roller Recommended | 4.89 | 586.8 | 15A (OK) | 6 | Ch1
TOTAL |  |  |  | 11 Motors |  |  | 4.89 | 586.8 |  |  |  | 6 × Shelly Pro Dual (2 motors each) | LAN/RS485 → Homey |  | 4.89 | 586.8 | See grouping | 6 | Total Devices Needed

## Schedule
RAC Development | Craig Engel RAC Inc. | 724 S. 1220 W. Hurricane UT
Tammy Engel | racinc19@gmail.com | Permit # PREP 23-440 | Permit
1267 N 1390 W St. George UT | 435-229-7360 | Plans | Plans
racinc19billing@gmail.com |  | Engineering | Engineering
435-229-4759 |  | Inspection | Inspection Docs
|  | Selections | Selections
Trade |  | Progress |  | Start | Days | Finish | Delay | Notes
-Duration |  | 94.1% |  | 2024-01-01 | 235 | 2024-08-23 | 128
Pre Construction |  | 100% |  | 2024-01-01 | 24 | 2024-01-25 | 0
Construction Documents |  | 100% |  | 2024-01-01 | 1 | 2024-01-01
Manual J |  | 100% |  | 2024-01-02 | 0 | 2024-01-01
Selection File |  | 100% |  | 2024-01-03 | 0 | 2024-01-01
Schedule File |  | 100% |  | 2024-01-04 | 0 | 2024-01-01
Civial Engineering |  | 100% |  | 2024-01-05 | 1 | 2024-01-05
Structural Engineering |  | 100% |  | 2024-01-06 | 1 | 2024-01-06
Permit |  | 100% |  | 2024-01-07 | 15 | 2024-01-25
Material Deposits |  | 100% |  | 2024-01-08 | 15 | 2024-01-26
Temp Power | I Tech Electric | 100% |  | 2024-01-08 | 1 | 2024-01-08
Job Sign |  | 100% |  | 2024-03-04 | 0 | 2024-01-08
Site Prep |  | 100% |  | 2024-01-26 | 10 | 2024-02-05 | 0
Survey |  | 100% |  | 2024-01-26 | 1 | 2024-01-26
Site Walls |  | 100% |  | 2024-01-29 | 5 | 2024-02-02
Dumpster |  | 100% |  | 2024-02-05 | 1 | 2024-02-05
Portable Toilet |  | 100% |  | 2024-02-06 | 0 | 2024-02-05
Temp Water |  | 100% |  | 2024-02-06 | 0 | 2024-02-05
Temp Electric Meter |  | 100% |  | 2024-02-06 | 0 | 2024-02-05
Foundation |  | 100% |  | 2024-01-01 | 78 | 2024-03-19 | 42
Strings | RG QUALITY CONCRETE | 100% |  | 2024-01-01 | 1 | 2024-01-01
Footing Dig |  | 100% |  | 2024-01-02 | 1 | 2024-01-02
Place Pea Gravel |  | 100% |  | 2024-01-03 | 1 | 2024-01-03
Footing Compaction Inspect |  | 100% |  | 2024-01-04 | 1 | 2024-01-04
Setting Forms |  | 100% |  | 2024-01-05 | 1 | 2024-01-05
Setting Rebar/Blockouts |  | 100% |  | 2024-01-08 | 1 | 2024-01-08 | 40
Underground Plumbing | MASTER PLUMBING SYSTEMS | 100% |  | 2024-03-04 | 2 | 2024-03-05
Plumbing Inspect |  | 100% |  | 2024-03-06 | 1 | 2024-03-06
Pour Footings |  | 100% |  | 2024-03-07 | 1 | 2024-03-07
Shade and fill | RG QUALITY CONCRETE | 100% |  | 2024-03-08 | 1 | 2024-03-08
Underground Electric |  | 100% |  | 2024-03-11 | 1 | 2024-03-11
Termite |  | 100% |  | 2024-03-11 | 0 | 2024-03-11
Slab inspection |  | 100% |  | 2024-03-12 | 1 | 2024-03-12
Place Gravel/Int Footing |  | 100% |  | 2024-03-13 | 1 | 2024-03-13 | 2
Place & tape Vapor |  | 100% |  | 2024-03-15 | 1 | 2024-03-15
Form Recess |  | 100% |  | 2024-03-15 | 0 | 2024-03-15
Slab Pour |  | 100% |  | 2024-03-18 | 1 | 2024-03-18
Garage/Recess Pour |  | 100% |  | 2024-03-19 | 1 | 2024-03-19
Strip and Close and grade |  | 100% |  | 2024-03-19 | 0 | 2024-03-19
Structure |  | 100% |  | 2024-03-20 | 12 | 2024-04-01 | 0
Notify Verify Truss | St. George Truss | 100% |  | 2024-03-20 | 1 | 2024-03-20
Deliver Wall Lumber | Sunpro | 100% |  | 2024-03-20 | 0 | 2024-03-20
Notify Gas Utilities |  | 100% |  | 2024-03-20 | 0 | 2024-03-20
Wall Framing |  | 100% |  | 2024-03-21 | 2 | 2024-03-22
Deliver Truss/Roof Wood | St. George Truss | 100% |  | 2024-03-25 | 1 | 2024-03-25
Roof Framing |  | 100% |  | 2024-03-26 | 2 | 2024-03-27
Deliver Punch Wood |  | 100% |  | 2024-03-28 | 1 | 2024-03-28
Framing Punch |  | 100% |  | 2024-03-29 | 2 | 2024-04-01
Deliver Drains & Piping | MASTER PLUMBING SYSTEMS | 100% |  | 2024-03-29 | 0 | 2024-04-01
Roof Drains | MASTER PLUMBING SYSTEMS | 100% |  | 2024-03-29 | 0 | 2024-04-01
Electrical Main | I Tech Electric | 100% |  | 2024-03-29 | 0 | 2024-04-01
Gas Stub |  | 100% |  | 2024-03-29 | 0 | 2024-04-01
Dry in |  | 100% |  | 2024-03-29 | 4 | 2024-04-02 | 0
Roofing IWS | Pierce Siding | 100% |  | 2024-03-29 | 1 | 2024-03-29
Deliver Exterior Doors | Sunpro | 100% |  | 2024-04-02 | 1 | 2024-04-02
Install Exterior Doors | Estimate# 3561 MVE Lot 6.pdf | 100% |  | 2024-04-02 | 0 | 2024-04-02
Deliver Windows | LP Building Solutions | 100% |  | 2024-04-02 | 0 | 2024-04-02
Install Exterior Glass | LP Building Solutions | 100% |  | 2024-04-02 | 0 | 2024-04-02
Deliver/Install Entry Doors | URBAN DOORS | 100% |  | 2024-04-02 | 0 | 2024-04-02
Rough/5Way |  | 100% |  | 2024-04-02 | 20 | 2024-04-22 | 2
Rough Mechanical | KUHNS HEATING & AIR | 100% |  | 2024-04-02 | 2 | 2024-04-06 | 1
Rough Plumbing/Gas/Roof Drains | MASTER PLUMBING SYSTEMS | 100% |  | 2024-04-08 | 2 | 2024-04-11 | 1
Rough Electrical | I Tech Electric | 100% |  | 2024-04-12 | 3 | 2024-04-18 | 0
Rough Gas |  | 100% |  | 2024-04-19 | 1 | 2024-04-19
5 Way |  | 100% |  | 2024-04-22 | 1 | 2024-04-22
Rough Punch |  | 100% |  | 2024-04-22 | 0 | 2024-04-22
Exterior Sealing |  | 100% |  | 2024-04-23 | 51 | 2024-06-13 | 9
Set Scaffold | SIPCO/BSM | 100% |  | 2024-04-23 | 1 | 2024-04-23
Hang Exterior Gyp | H&E DRYWALL | 100% |  | 2024-04-24 | 1 | 2024-04-24
Lath | SIPCO/BSM | 100% |  | 2024-04-24 | 0 | 2024-04-24
Lath Inspection |  | 100% |  | 2024-04-25 | 1 | 2024-04-25
Brown |  | 100% |  | 2024-04-26 | 2 | 2024-05-13 | 9
Color |  | 100% |  | 2024-05-14 | 3 | 2024-05-17
Gas Meter |  | 100% |  | 2024-05-20 | 1 | 2024-05-20
Exterior Stone |  | 100% |  | 2024-05-21 | 3 | 2024-05-24
Cladding Metal | Broken Horn Welding | 100% |  | 2024-05-27 | 5 | 2024-06-03
Silicone |  | 100% |  | 2024-06-04 | 2 | 2024-06-06
Roofing Metal |  | 100% |  | 2024-06-07 | 2 | 2024-06-11
Dimple Mat |  | 100% |  | 2024-06-12 | 1 | 2024-06-12
Ballast |  | 100% |  | 2024-06-13 | 1 | 2024-06-13
Insulation Wall Substrate |  | 98.75% |  | 2024-04-23 | 43 | 2024-06-05 | 3
Net & Blow | LP Building Solutions | 100% |  | 2024-04-23 | 2 | 2024-04-25
Insulation Inspection |  | 100% |  | 2024-04-26 | 1 | 2024-04-26
Install Trim |  | 100% |  | 2024-04-29 | 3 | 2024-05-02
Delivery Drywall | H&E DRYWALL | 100% |  | 2024-05-03 | 1 | 2024-05-03
Hang |  | 100% |  | 2024-05-06 | 4 | 2024-05-13 | 1
Blower Door |  | 100% |  | 2024-05-06 | 0 | 2024-05-06
Tape & Texture |  | 100% |  | 2024-05-07 | 11 | 2024-05-22
Shelfing |  | 100% |  | 2024-05-23 | 1 | 2024-05-23
Paint | RED HILLS PAINTING | 100% |  | 2024-05-28 | 5 | 2024-06-04 | 2
Permanent Power | I Tech Electric | 100% |  | 2024-05-28 | 0 | 2024-05-28
Garage Door | LP Building Solutions | 100% |  | 2024-05-28 | 0 | 2024-05-28
Set HVAC | KUHNS HEATING & AIR | 85% |  | 2024-05-29 | 5 | 2024-06-05
Interior Floor/Tile/Carpentry |  | 99.7% |  | 2024-06-05 | 47 | 2024-07-22 | 0
Deliver Tile |  | 100% |  | 2024-06-05 | 1 | 2024-06-05
Tile Floor |  | 100% |  | 2024-06-06 | 11 | 2024-06-21
Paint Trim |  | 100% |  | 2024-06-24 | 2 | 2024-06-26
Cabinets/Laminate | BOARDWALK CABINETRY | 97% |  | 2024-06-27 | 5 | 2024-07-04
Template | COUNTERTOP SOURCE | 100% |  | 2024-07-05 | 1 | 2024-07-05
Shower Surrounds |  | 100% |  | 2024-07-08 | 10 | 2024-07-22
Set Fireplace |  | 100% |  | 2024-07-08 | 0 | 2024-07-08
Measure Glass |  | 100% |  | 2024-07-09 | 1 | 2024-07-09
Hardware |  | 100% |  | 2024-07-10 | 1 | 2024-07-10
Countertop | COUNTERTOP SOURCE | 100% |  | 2024-07-11 | 1 | 2024-07-11
Hardscape/Landscape |  | 69.38% |  | 2024-06-03 | 25 | 2024-06-28 | 0
Rough Grade |  | 100% |  | 2024-06-03 | 1 | 2024-06-03
Site Walls |  | 100% |  | 2024-06-04 | 2 | 2024-06-06
Drains & Sleeves |  | 100% |  | 2024-06-07 | 1 | 2024-06-07
Hardscape |  | 100% |  | 2024-06-10 | 5 | 2024-06-17
Landscape/Fountains |  | 55% |  | 2024-06-18 | 5 | 2024-06-25
Signs |  | 0% |  | 2024-06-26 | 1 | 2024-06-26
Sewer |  | 0% |  | 2024-06-27 | 1 | 2024-06-27
BackFlow |  | 100% |  | 2024-06-28 | 1 | 2024-06-28
Home Stretch |  | 65.4% |  | 2024-07-10 | 44 | 2024-08-23 | 8
Deliver Electrical Fixtures |  | 100% |  | 2024-07-10 | 1 | 2024-07-10
Electrical Trim | I Tech Electric | 85% |  | 2024-07-24 | 5 | 2024-07-31 | 9
Deliver Plumbing Fixtures |  | 100% |  | 2024-07-24 | 0 | 2024-07-24
Plumbing Trim | MASTER PLUMBING SYSTEMS | 95% |  | 2024-07-24 | 5 | 2024-07-31 | -1
Install Salt Brick |  | 100% |  | 2024-08-01 | 1 | 2024-08-01
Install Acrylic |  | 100% |  | 2024-08-01 | 0 | 2024-08-01
Install Stretch |  | 100% |  | 2024-08-01 | 0 | 2024-08-01
Install Wall Panels |  | 0% |  | 2024-08-01 | 0 | 2024-08-01
Install Mirror |  | 100% |  | 2024-08-01 | 0 | 2024-08-01
Blower Door |  | 100% |  | 2024-08-02 | 1 | 2024-08-02
Final Clean |  | 66% |  | 2024-08-05 | 1 | 2024-08-05
Appliance |  | 35% |  | 2024-08-06 | 1 | 2024-08-06
CO |  | 0% |  | 2024-08-07 | 1 | 2024-08-07
Punch Walk |  | 0% |  | 2024-08-08 | 1 | 2024-08-08
Punch Completion |  | 0% |  | 2024-08-09 | 10 | 2024-08-23
Formulas:
Start = min([Start, row below]:E135)
Start = workday([Finish, row above],1)
Finish = MAX([Finish, row below]:G135)
Finish = if([Days]=0,[Finish, row above], workday([Start],[Days]-1))+WORKDAY([Delay],[Delay, row above])

## Tammy
Who is it Yes I meet that bunch of real cast like you know you got to watch you I this guy Got fucking indigestion from the sugar Yep Well yeah I feel like I know I've stabbed you you It's not too long that's just not fair to me Oh Whoops | Budget | Date
|  |  | Draw 1 | Draw 2 | Draw 3 | Draw 4 | Draw 5 | Draw 6 | Draw 7 | Draw 8 | Draw 9 | Draw 10 | Draw 11 | Draw 12 | Draw 13 | Draw 14 | Draw 15 | Draw 16 | Draw 17
| Budget | Outstanding
| 2775448.51 | -2774723.51 | 725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Deposit
Plumbing Fixtures | 17000 | -17000
Electrical Fixtures | 18000 | -18000
Hidden Door | 25000 | -25000
Vault Door | 7500 | -7500
Cabinet | 26000 | -26000
Entry Stair | 17000 | -17000
Tile Material | 80000 | -80000
Rammed Earth | 50000 | -50000
Exterior Glass | 115000 | -115000
Rammed earth Material | 45000 | -45000
Railing | 46000 | -46000
Range | 95000 | -95000
Permiting
Facilities | 10000 | -10000
Permits | 30000 | -29275 | Draw 1: 725
Builders Risk | 5000 | -5000
Manual J | 1500 | -1500
Plans | 1000 | -1000
Soil | 3000 | -3000
Inspections | 2500 | -2500
Site Utilities
Site Utilities | 122000 | -122000
Gas | 10000 | -10000
Power | 5000 | -5000
Water | 5000 | -5000
Structural
Ftgs | 35710.41 | -35710.41
Wall | 63078 | -63078
Slab | 49345.1 | -49345.1
Pan | 32075 | -32075
Site | 9640 | -9640
Pretreat | 1000 | -1000
Steel | 184000 | -184000
Lumber | 50000 | -50000
Framing Labor | 80600 | -80600
Truss | 40000 | -40000
Mechanical Rough
HVAC/ERV | 32000 | -32000
Plumbing/Gas | 25000 | -25000
Electrical | 45000 | -45000
AV | 80000 | -80000
Solar | 25000 | -25000
Fireplace | 22500 | -22500
Exterior Sealing
Roofing | 35000 | -35000
Coatings | 102000 | -102000
Exterior Glass | 115000 | -115000
Exterior Doors | 13000 | -13000
Garage Door | 22500 | -22500
Exterior Stucco | 60000 | -60000
Stone Veneer | 30000 | -30000
Rammed Earth | 50000 | -50000
Wall/Cieling Finish
Insulation | 40000 | -40000
Sheetrock | 41500 | -41500
Paint | 23000 | -23000
Tile Labor | 53000 | -53000
Carpentery
Cabinet | 26000 | -26000
Countertops | 45000 | -45000
Finish Carpentry | 12000 | -12000
Door | 28500 | -28500
Base&Case | 5000 | -5000
Door & Bath Hardware | 5000 | -5000
Entry Stair | 17000 | -17000
Wood Stair | 5000 | -5000
Stair Labor | 10000 | -10000
Vault Door | 7500 | -7500
Hidden Door | 25000 | -25000
Equipment/ Finishes
HVAC/ERV | 21500 | -21500
Plumbing/Gas | 32000 | -32000
Electrical | 45000 | -45000
AV | 80000 | -80000
Range | 95000 | -95000
Appliance | 48000 | -48000
Glass | 7500 | -7500
Railing | 46000 | -46000
Outdoor | 60000 | -60000
Cleaning | 5000 | -5000
Landscape
Solar | 25000 | -25000
Landscape |  | 0
Pavers | 28000 | -28000
0
Options
Steam
Floor Heat

## Budget (hidden)
Trade | Sub | Bid Amount | Comment
Total
Lot 34
Sq Ft | 2345
Cost per Ft. | 0
LTV | 0%
Gross | 15% | 295216.99 | 723091.55 | 785000 | 70%
Realtor | 5% | 40000 | 39250
Profit | 10% | 80000
Land |  | 175000 | 175000
Build Cost |  | 216.99 | 508841.55 | 549500
Interest
Origination | 1%
Contingency
Facilities |  | 1.81 | 4244.45
Engineering |  | 1.27 | 2978.15
Permits | City of Hurricane | 6.4 | 15008
Builder Risk |  | 1.81 | 4244.45
Legal |  | 1.81 | 4244.45
WCD |  | 4.27 | 10013.15
Plans | Steamroller | 0.18 | 422.1
Recorder |  | 0.05 | 117.25
Soil | Landmark | 0.54 | 1266.3
Inspections |  | 0.54 | 1266.3
SWPPP |  | 0.54 | 1266.3
Pad Prep |  | 2.72 | 6378.4
Concrete | Dixie, Ceasar, Sunset | 12.69 | 29758.05
Pretreat | Morgan Pest Control | 0.27 | 633.15
Lumber | Sunpro | 7.25 | 17001.25
Framing Labor | BW, 5 DI, Bud | 9.07 | 21269.15
Truss | SGT Truss | 5.44 | 12756.8
0
Plumbing/Gas | Bringhurst, Master | 9.95 | 23332.75
Plumbing Fixtures | RAC | 2.99 | 7011.55
Water Heater | RAC |  | 0
Water Filtration | Advanced | 2.86 | 6706.7
HVAC | Kuhn's/Crofts | 5.73 | 13436.85
Fireplace | Dixie | 2.56 | 6003.2
Electrical | DHE.Copper.Breck | 7.25 | 17001.25
Electrical Fixtures | RAC | 3.63 | 8512.35
0
Roofing | Pierce | 10.88 | 25513.6
Windows | LP | 9.79 | 22957.55
Entry Door |  | 2.72 | 6378.4
Exterior Doors | Sunpro | 1.28 | 3001.6
Rainscreen | RAC | 1.09 | 2556.05
Exterior Stucco | D&D | 10.73 | 25161.85
Stone Veneer | Kent | 5.44 | 12756.8
0
Insulation | LP | 5.44 | 12756.8
Shadow Trim | RAC | 0.91 | 2133.95
Finish Carpentry | A&L | 1.27 | 2978.15
Sheetrock | D&D | 9.03 | 21175.35
Flooring/Tile | Potter | 5.44 | 12756.8
Floor Polish | KC | 0.64 | 1500.8
Floor Protection | RAC | 0.64 | 1500.8
Paint | D&D | 3.44 | 8066.8
0
Garage Door | Jesco | 3.36 | 7879.2
Cabinet | Boardwalk | 14.51 | 34025.95
Countertops | Countertop source | 5.44 | 12756.8
Interior Door | Sunpro | 3.2 | 7504
Interior trim material | Sunpro | 1.49 | 3494.05
Door & Bath Hardware | Sunpro | 1.07 | 2509.15
Closet | A&L | 1.81 | 4244.45
0
Glass | Desert | 1.81 | 4244.45
Painted Glass | Desert | 2.72 | 6378.4
Stretch | RAC/H&E | 1.81 | 4244.45
Alabaser | RAC/Desert | 2.13 | 4994.85
Salt | RAC/Quick | 2.13 | 4994.85
0
Cleaning | Laura | 0.91 | 2133.95
Appliance | Ferguson's | 6.53 | 15312.85
0
Exterior concrete | Dixie, Ceasar, Sunset | 4.07 | 9544.15
Landscape | Bruce | 3.63 | 8512.35